## Overview
Module / Feature | Platform | Task Description | Output / Deliverable | Owner | Priority | Status | Start Date | Due Date | Dependencies | Notes
Project Setup | All | Initialize repos, environments, CI/CD | Repos + CI pipelines |  | High | Planned
Authentication | All | End-to-end auth across apps | Login/Signup/JWT flow |  | High | Planned |  |  | Project Setup
User Management | All | CRUD for users/roles/permissions | Users & Roles modules |  | High | Planned |  |  | Authentication
Dashboard | All | Initial KPIs & navigation | Dashboard screens/APIs |  | Medium | Planned |  |  | Auth, Base UI
Settings | All | Profile, app settings | Settings screens & endpoints |  | Medium | Planned |  |  | User Management

## Frontend (Vue)
Module / Feature | Platform | Task Description | Output / Deliverable | Deliverable Git Ver | Dependencies | Notes
Project Setup | Frontend (Vue) | Create Vue 3 + Vite project, ESLint + Prettier | Vue project skeleton |  |  | Use Tailwind or Vuetify
Project Setup | Frontend (Vue) | Define folder structure (views/components/store/api) | Folder structure documented
UI Framework | Frontend (Vue) | Install and configure UI framework (Element Plus/Vuetify/Tailwind) | UI base theme |  | Project Setup
Core Components | Frontend (Vue) | Build Navbar, Sidebar, Footer, Loader, Modal | Reusable components |  | UI Framework
Routing & Guards | Frontend (Vue) | Set up Vue Router with auth guard and public/private routes | router/index.ts |  | Authentication API
State Mgmt | Frontend (Vue) | Set up Pinia store for auth/user/app state | store modules |  | Routing & Guards
Auth Screens | Frontend (Vue) | Implement Login view and logout logic | LoginView.vue |  | Auth API ready | Token persisted in storage
Feature: Dashboard | Frontend (Vue) | Implement Dashboard view with sample KPIs | DashboardView.vue |  | Core Components, API stubs
Feature: Users | Frontend (Vue) | User list, detail, create/edit forms | UsersList.vue, UserForm.vue |  | User endpoints
Feature: Settings | Frontend (Vue) | Profile & app settings UI | SettingsView.vue |  | Auth, Users
API Integration | Frontend (Vue) | Configure Axios with baseURL and interceptors (401 refresh) | api/http.ts |  | Backend auth endpoints
Testing | Frontend (Vue) | Set up Vitest + component tests | Test suite & reports |  | Core components
Build & Deploy | Frontend (Vue) | Optimize build and add deploy script | Vite build + CI job |  | CI/CD base

## Backend (Python)
Module / Feature | Platform | Task Description | Output / Deliverable | Deliverable Git Ver | Dependencies | Notes
Project Setup | Backend (Python) | Initialize FastAPI/Django project with poetry/venv | Backend project skeleton
DB Config | Backend (Python) | Connect PostgreSQL, Alembic/Django migrations | DB connection + migrations |  | Project Setup
Auth Module | Backend (Python) | JWT auth: login, refresh, logout | /auth/login, /auth/refresh |  | DB Config | Use passlib, pyjwt
User Module | Backend (Python) | CRUD for users, roles, permissions | /users endpoints |  | Auth Module
Models | Backend (Python) | Define User, Role, Permission, AuditLog models | ORM models + migrations |  | DB Config
Services | Backend (Python) | Email service, file upload service | Service layer modules |  | Models
Background Jobs | Backend (Python) | Configure Celery/RQ for async tasks | Worker + broker config |  | Services | Redis/RabbitMQ
Observability | Backend (Python) | Logging, request tracing, metrics endpoints | Log config + /health |  | Project Setup
Docs | Backend (Python) | Auto-generate OpenAPI/Swagger + examples | Swagger/Redoc available |  | Auth/User endpoints
Tests | Backend (Python) | Unit & integration tests for endpoints | Coverage report |  | Core modules
Deploy | Backend (Python) | Dockerfile, Gunicorn/Uvicorn, Nginx config | Container image + config |  | Project Setup | CI/CD integration

## Mobile (Flutter)
Module / Feature | Platform | Task Description | Output / Deliverable | Deliverable Git Ver | Dependencies | Notes
Project Setup | Mobile (Flutter) | Initialize Flutter project, flavors (dev/stage/prod) | Flutter skeleton
State Mgmt | Mobile (Flutter) | Choose and configure Provider/Riverpod/Bloc | State mgmt setup |  | Project Setup
Core UI | Mobile (Flutter) | Theme, typography, reusable widgets (Button, Input, Modal) | lib/ui/components/* |  | State Mgmt
Navigation | Mobile (Flutter) | Set up GoRouter/Navigator 2.0 routes | Router config |  | Core UI
Auth Screens | Mobile (Flutter) | Login/Signup/Forgot password screens | lib/features/auth/* |  | Auth API | Use flutter_secure_storage
Feature: Dashboard | Mobile (Flutter) | Implement dashboard with sample KPIs | lib/features/dashboard/* |  | Core UI, API stubs
Feature: Profile | Mobile (Flutter) | Profile view & edit | lib/features/profile/* |  | Auth, Users
API Integration | Mobile (Flutter) | Dio setup, interceptors, error wrapper | lib/data/api/* |  | Backend auth endpoints
Device Integrations | Mobile (Flutter) | Camera/GPS/File picker (as required) | Plugins configured |  | Feature needs
Push Notifications | Mobile (Flutter) | Configure Firebase Messaging | Notifications working |  | Firebase setup
Testing & Release | Mobile (Flutter) | Widget tests, Android/iOS build pipelines | Builds + test report |  | Project Setup | Store prep later

## Combined Backlog
Module / Feature | Platform | Task Description | Output / Deliverable | Owner | Priority | Status | Start Date | Due Date | Dependencies | Notes
Project Setup | All | Initialize repos, environments, CI/CD | Repos + CI pipelines |  | High | Planned
Authentication | All | End-to-end auth across apps | Login/Signup/JWT flow |  | High | Planned |  |  | Project Setup
User Management | All | CRUD for users/roles/permissions | Users & Roles modules |  | High | Planned |  |  | Authentication
Dashboard | All | Initial KPIs & navigation | Dashboard screens/APIs |  | Medium | Planned |  |  | Auth, Base UI
Settings | All | Profile, app settings | Settings screens & endpoints |  | Medium | Planned |  |  | User Management
Project Setup | Frontend (Vue) | Create Vue 3 + Vite project, ESLint + Prettier | Vue project skeleton |  | High | Planned |  |  |  | Use Tailwind or Vuetify
Project Setup | Frontend (Vue) | Define folder structure (views/components/store/api) | Folder structure documented |  | High | Planned
UI Framework | Frontend (Vue) | Install and configure UI framework (Element Plus/Vuetify/Tailwind) | UI base theme |  | High | Planned |  |  | Project Setup
Core Components | Frontend (Vue) | Build Navbar, Sidebar, Footer, Loader, Modal | Reusable components |  | High | Planned |  |  | UI Framework
Routing & Guards | Frontend (Vue) | Set up Vue Router with auth guard and public/private routes | router/index.ts |  | High | Planned |  |  | Authentication API
State Mgmt | Frontend (Vue) | Set up Pinia store for auth/user/app state | store modules |  | High | Planned |  |  | Routing & Guards
Auth Screens | Frontend (Vue) | Implement Login view and logout logic | LoginView.vue |  | High | Planned |  |  | Auth API ready | Token persisted in storage
Feature: Dashboard | Frontend (Vue) | Implement Dashboard view with sample KPIs | DashboardView.vue |  | Medium | Planned |  |  | Core Components, API stubs
Feature: Users | Frontend (Vue) | User list, detail, create/edit forms | UsersList.vue, UserForm.vue |  | High | Planned |  |  | User endpoints
Feature: Settings | Frontend (Vue) | Profile & app settings UI | SettingsView.vue |  | Medium | Planned |  |  | Auth, Users
API Integration | Frontend (Vue) | Configure Axios with baseURL and interceptors (401 refresh) | api/http.ts |  | High | Planned |  |  | Backend auth endpoints
Testing | Frontend (Vue) | Set up Vitest + component tests | Test suite & reports |  | Medium | Planned |  |  | Core components
Build & Deploy | Frontend (Vue) | Optimize build and add deploy script | Vite build + CI job |  | Medium | Planned |  |  | CI/CD base
Project Setup | Backend (Python) | Initialize FastAPI/Django project with poetry/venv | Backend project skeleton |  | High | Planned
DB Config | Backend (Python) | Connect PostgreSQL, Alembic/Django migrations | DB connection + migrations |  | High | Planned |  |  | Project Setup
Auth Module | Backend (Python) | JWT auth: login, refresh, logout | /auth/login, /auth/refresh |  | High | Planned |  |  | DB Config | Use passlib, pyjwt
User Module | Backend (Python) | CRUD for users, roles, permissions | /users endpoints |  | High | Planned |  |  | Auth Module
Models | Backend (Python) | Define User, Role, Permission, AuditLog models | ORM models + migrations |  | High | Planned |  |  | DB Config
Services | Backend (Python) | Email service, file upload service | Service layer modules |  | Medium | Planned |  |  | Models
Background Jobs | Backend (Python) | Configure Celery/RQ for async tasks | Worker + broker config |  | Medium | Planned |  |  | Services | Redis/RabbitMQ
Observability | Backend (Python) | Logging, request tracing, metrics endpoints | Log config + /health |  | Medium | Planned |  |  | Project Setup
Docs | Backend (Python) | Auto-generate OpenAPI/Swagger + examples | Swagger/Redoc available |  | High | Planned |  |  | Auth/User endpoints
Tests | Backend (Python) | Unit & integration tests for endpoints | Coverage report |  | Medium | Planned |  |  | Core modules
Deploy | Backend (Python) | Dockerfile, Gunicorn/Uvicorn, Nginx config | Container image + config |  | High | Planned |  |  | Project Setup | CI/CD integration
Project Setup | Mobile (Flutter) | Initialize Flutter project, flavors (dev/stage/prod) | Flutter skeleton |  | High | Planned
State Mgmt | Mobile (Flutter) | Choose and configure Provider/Riverpod/Bloc | State mgmt setup |  | High | Planned |  |  | Project Setup
Core UI | Mobile (Flutter) | Theme, typography, reusable widgets (Button, Input, Modal) | lib/ui/components/* |  | High | Planned |  |  | State Mgmt
Navigation | Mobile (Flutter) | Set up GoRouter/Navigator 2.0 routes | Router config |  | High | Planned |  |  | Core UI
Auth Screens | Mobile (Flutter) | Login/Signup/Forgot password screens | lib/features/auth/* |  | High | Planned |  |  | Auth API | Use flutter_secure_storage
Feature: Dashboard | Mobile (Flutter) | Implement dashboard with sample KPIs | lib/features/dashboard/* |  | Medium | Planned |  |  | Core UI, API stubs
Feature: Profile | Mobile (Flutter) | Profile view & edit | lib/features/profile/* |  | Medium | Planned |  |  | Auth, Users
API Integration | Mobile (Flutter) | Dio setup, interceptors, error wrapper | lib/data/api/* |  | High | Planned |  |  | Backend auth endpoints
Device Integrations | Mobile (Flutter) | Camera/GPS/File picker (as required) | Plugins configured |  | Medium | Planned |  |  | Feature needs
Push Notifications | Mobile (Flutter) | Configure Firebase Messaging | Notifications working |  | Medium | Planned |  |  | Firebase setup
Testing & Release | Mobile (Flutter) | Widget tests, Android/iOS build pipelines | Builds + test report |  | High | Planned |  |  | Project Setup | Store prep later